## iTHRIVE Background
i-THRIVE Implementation Plan
The steps outlined in this implementation plan template mirror the phases of the i-THRIVE Approach to Implementation which is an evidence based approach to implementation to enable better delivery of system change.
An overview of the i-THRIVE Approach to Implementation is set out below:
For further information about i-THRIVE and support with implementation please visit www.implementingTHRIVE.org.

## Implementation Plan
Greater Manchester THRIVE Implementation Plan
[7 empty] | 2018_19 |  |  |  | 2019_20 |  |  |  | 2020_21 |  |  |  | 2021_22
|  | Notes / Resources Available | Responsibility/Task Owner | Start Date | Finish Date | Status | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Year Five |  |  |  | Comments
[7 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Set Up
0.1 | Establish cross sector approval to proceed with i-THRIVE |  |  | 2018-04-01 | 2018-06-30 | Complete | bar: Q1
0.2 | Have a named lead for implementing THRIVE |  |  | 2018-07-01 | 2018-09-30 | bar: Q2
0.3 | Set up multi-agency Programme Board (include senior leadership from CCG, health provider(s), local authority, education, third sector) | Support from i-THRIVE PMO |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.4 | Undertake stakeholder mapping | Support from i-THRIVE PMO |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.5 | Create communications and engagement plan based on stakeholder analysis | Support from i-THRIVE PMO |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.6 | Multi-agency working group established | i-THRIVE Toolkit |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.7 | Site leads/sponsors identified (where i-THRIVE delivered across multiple sites) |  |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.8 | Establish communications functions (contact databases, shared folders, website) | Support from i-THRIVE PMO |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.9 | Create high level project plan | i-THRIVE Toolkit |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
0.10 | High level project plan approved by Programme Board |  |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1 | i-THRIVE Approach to Implementation Phase 1: Engagement, Understanding and Planning
1.1 | Key messaging for i-THRIVE project established - goals, aspirations, local context |  |  | 2018-07-01 | 2018-12-31 | On Target | bar: Q2 to Q3
1.2 | Whole system stakeholder engagement event | i-THRIVE Toolkit |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.3 | Pathway mapping workshop | i-THRIVE Toolkit |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.4 | Staff consultation | i-THRIVE Toolkit |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.5 | Young people and families consultation |  |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.6 | Review Quantitative data and fill gaps | bar: Q3
1.7 | Qualitative review of feedback collected |  |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.8 | Service performance review (including population need, demand, flow, experience of service, participation levels, clinical outcomes, efficiency, current shared decision making practice etc) | i-THRIVE Toolkit |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.9 | Mapping of current outcome measures used across health, social care, education and voluntary sector |  |  | 2018-10-01 | 2018-12-31 | Not due to start | bar: Q3
1.1 | Understanding your data workshop | i-THRIVE Toolkit |  | 2019-01-01 | 2019-03-31 | Not due to start | bar: Q4
1.11 | THRIVE Assessment Tool workshop | i-THRIVE Toolkit |  | 2019-01-01 | 2019-06-30 | Not due to start | bar: Q4 to Q1
1.12 | Engagement with wider system re THRIVE-like baseline score |  |  | 2018-10-01 | 2019-03-31 | Not due to start | bar: Q1
1.13 | Prioritisation and gap analysis workshop | i-THRIVE Toolkit |  | 2019-04-01 | 2019-06-30 | Not due to start | bar: Q1
1.14 | Redesign workshop | i-THRIVE Toolkit |  | 2019-07-01 | 2019-09-30 | Not due to start | bar: Q2
1.15 | Creation of local model for i-THRIVE |  |  | 2019-07-01 | 2019-09-30 | Not due to start | bar: Q2
1.16 | Finalise implementation plan | i-THRIVE Toolkit |  | 2019-07-01 | 2019-09-30 | Not due to start | bar: Q2
2 | i-THRIVE Approach to Implementation Phase 2: Building Capacity
2.1 | Review of staff skills for THRIVE-like working |  |  | 2018-10-01 | 2019-01-01 | Not due to start | bar: Q3 to Q4
2.2 | Review of staff capacity for delivery of new model |  |  | 2019-07-01 | 2019-12-31 | Not due to start | bar: Q2 to Q3
2.3 | Plan for recruiting to deliver new model |  |  | 2019-10-01 | 2019-12-31 | Not due to start | bar: Q3
2.4 | Review of training opportunities available across all organisations |  |  | 2019-10-01 | 2019-12-31 | Not due to start | bar: Q3
2.5 | Creation of workforce development plan |  |  | 2019-10-01 | 2019-03-31 | Not due to start | bar: Q3 to Q4
2.6 | Development of new commissioning specification |  |  | 2019-04-01 | 2020-03-31 | Not due to start | bar: Q1 to Q4
2.7 | Identification and creation of local champions and implementation leads |  |  | 2019-01-01 | 2019-06-30 | Not due to start | bar: Q4 to Q1
2.8 | Training for implementation leads (knowledge of change management, i-THRIVE Approach to Implementation and QI) | i-THRIVE Academy |  | 2019-04-01 | 2019-12-31 | Not due to start | bar: Q1 to Q3
2.9 | i-THRIVE Academy training for multi-agency front line staff and managers | i-THRIVE Academy |  | 2019-01-01 | 2021-03-31 | Not due to start
| - Shared decision making | i-THRIVE Academy |  | 2019-01-01 | 2021-03-31 | Not due to start
| - Getting Advice and Signposting | i-THRIVE Academy |  | 2019-01-01 | 2021-03-31 | Not due to start
| - When to stop treatment | i-THRIVE Academy |  | 2019-01-01 | 2021-03-31 | Not due to start
| - Risk Support | i-THRIVE Academy |  | 2019-01-01 | 2021-03-31 | Not due to start
| - i-THRIVE Grids | i-THRIVE Academy |  | 2019-01-01 | 2021-03-31 | Not due to start
| ACE / Trauma training | GM ithrive team |  | 2019-01-01 | 2021-03-31
2.1 | Multi-agency workshop event to reflect on learnings from i-THRIVE Academy and other training |  |  | 2019-04-01 | 408888 | Not due to start | bar: Q1
2.11 | Delivery of other training and development as set out in workforce development plan |  |  | 2019-04-01 | - | Not due to start | bar: Q1 to Q4
2.12 | Review of workforce development delivery and plans for ongoing work |  |  | 2020-04-01 | - | Not due to start | bar: Q1 to Q4
3 | i-THRIVE Approach to Implementation Phase 3: Implementation
3.1 | Ongoing review of implementation plan agreed at end of phase one |  |  | 2018-10-01 | - | Not due to start | bar: Q3 to Q4
3.2 | Detailed implementation planning finalised with lead for each project identified |  |  | 2019-01-01 | 2019-03-31 | Not due to start | bar: Q4
3.3 | Delivery of implementation plan as specified *import detailed implementation plan into this section* The implementation plan should include - as a minimum - the following elements which are required in order for a site to be assessed as 'THRIVE-like' in line with the THRIVE Assessment Tool: | i-THRIVE Toolkit |  | 2019-01-01 | - | Not due to start
| > Children and young people's mental health is included in the LTP and the STP and implementation plan is in place for delivering outcomes |  |  | 2019-01-01 | - | Not due to start
| > Multi-agency strategy and policy for delivering improved outcomes for children and young people's mental health operational with clear and measureable goals |  |  | 2019-01-01 | - | Not due to start
| > Multi-agency commissioning board operational with joint accountability for delivering strategy |  |  | 2019-01-01 | - | Not due to start
| > Shared outcome framework for the multi-agency commissioning board is in place |  |  | 2019-01-01 | - | Not due to start
| > Annual commissioning cycle (multi-agency) operational supported by formal mechanism for service performance, outcome and preference data to inform the process |  |  | 2019-01-01 | - | Not due to start
| > Joint budgets to support delivery of strategy established with processes in place across all involved agencies |  |  | 2019-01-01 | - | Not due to start
| > Protocols established for regular sharing of performance and outcomes data across all agencies and commissioners |  |  | 2019-01-01 | - | Not due to start
| > Introduction of systematic preference data collection across all agencies and sectors |  |  | 2019-01-01 | - | Not due to start
| > All QI projects are undertaken using recognised methodology |  |  | 2019-01-01 | - | Not due to start
| > Outcomes and process measures are collected routinely and this data is used to help shape service provision, manage performance and deliver interventions **full list of measures is available from i-THRIVE programme team |  |  | 2019-01-01 | - | Not due to start
| > Local pathways structured to deliver care according to five THRIVE needs based groups |  |  | 2019-01-01 | - | Not due to start
| > Multi-agency assessment that categorises children and young people into the THRIVE needs based groups is operational |  |  | 2019-01-01 | - | Not due to start
| > THRIVE needs based group recorded for all cases |  |  | 2019-01-01 | - | Not due to start
| > Implementation of i-THRIVE Grids to support shared decision making |  |  | 2019-01-01 | - | Not due to start
| > Record of shared decision making documented for all cases |  |  | 2019-01-01 | - | Not due to start
| > Population health and wellbeing offer available to all children and young people |  |  | 2019-01-01 | - | Not due to start
| > Targeted prevention and resilience building offer available to children and young people who we know are more likely to require support with their mental health and wellbeing |  |  | 2019-01-01 | - | Not due to start
| > Digital front end is available for children, young people and their families |  |  | 2019-01-01 | - | Not due to start
| > There is a self-help and peer support offer available to children, young people and families |  |  | 2019-01-01 | - | Not due to start
| > Senior mental health practitioners (band 8 or above) involved in all advice and signposting |  |  | 2019-01-01 | - | Not due to start
| > Digitally enabled database of full range of community providers is operational |  |  | 2019-01-01 | - | Not due to start
| > In reach from CAMHS to schools is operational |  |  | 2019-01-01 | - | Not due to start
| > In reach from CAMHS to primary care is operational |  |  | 2019-01-01 | - | Not due to start
| > CAMHS outreach to hard to reach groups is operational |  |  | 2019-01-01 | - | Not due to start
| > Evidence of families being involved in development of care plans in all cases |  |  | 2019-01-01 | - | Not due to start
| > Evidence of therapy being aligned with NICE guidance for all cases |  |  | 2019-01-01 | - | Not due to start
| > Recorded note of treatment goals and expected outcomes for all cases |  |  | 2019-01-01 | - | Not due to start
| > Children, young people and their families are managed within the recommended number of therapy sessions |  |  | 2019-01-01 | - | Not due to start
| > Reasons for ending proforma completed for all cases with treatment |  |  | 2019-01-01 | - | Not due to start
| > Multi-agency structures and protocols for providing risk support |  |  | 2019-01-01 | - | Not due to start
| > Multi-agency THRIVE plans documented for all risk support cases |  |  | 2019-01-01 | - | Not due to start
3.4 | Year one of implementation (details to be added) |  |  | 2019-01-01 | 2019-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2019-01-01 | 2019-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2019-01-01 | 2019-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2019-01-01 | 2019-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2019-01-01 | 2019-12-31 | Not due to start | bar: Q4 to Q3
3.5 | Year one progress review and refine plan for year two |  |  | 2019-07-01 | 2020-03-31 | Not due to start | bar: Q2 to Q4
3.6 | Year two of implementation (details to be added) |  |  | 2020-01-01 | 2020-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2020-01-01 | 2020-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2020-01-01 | 2020-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2020-01-01 | 2020-12-31 | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2020-01-01 | 2020-12-31 | Not due to start | bar: Q4 to Q3
3.7 | Year two progress review and refine plan for year three |  |  | 2020-07-01 | 2021-03-31 | Not due to start | bar: Q2 to Q4
3.8 | Year three of implementation (details to be added) |  |  | 2021-01-01 | - | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2021-01-01 | - | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2021-01-01 | - | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2021-01-01 | - | Not due to start | bar: Q4 to Q3
| *add individual QI projects* |  |  | 2021-01-01 | - | Not due to start | bar: Q4 to Q3
3.9 | Year three progress review and refine plan for year four |  |  | - | - | Not due to start | bar: Q2 to Q4
3.1 | * Continue as necessary in yearly cycles* | bar: Q4
4 | i-THRIVE Approach to Implementation Phase 4: Embedding and Sustaining
4.1 | Establish learning collaborative | i-THRIVE Community of Practice model |  | 2017-07-01 | 408432 | Complete | bar: Q2 to Q4
4.2 | Learning collaborative |  |  | - | - | On Target | bar: Q4; Q2; Q4; Q2; Q4; Q2; Q4; Q2; Q4
4.3 | Embedding and sustaining year one implementation projects | Based on Normalisation Process Theory | bar: Q2 to Q4
4.4 | Embedding and sustaining year two implementation projects | bar: Q4 to Q4
4.5 | Embedding and sustaining year three implementation projects | bar: Q2 to Q4

## Communication Strategy
Communication Strategy
[Use this document to describe and monitor the communication plan for the project]
No. | Form of communication e.g. Verbal, Website, Blog, Newsletter etc | Description/Key Messages | Frequency | Responsibility | Audience | Start Date (DD/MM/YY) | End Date (DD/MM/YY) | Monitoring - confirm complete or record actions to correct

## Stakeholder Engagement
Stakeholder Engagement Plan
[Use this document to outline who is impacted by this project and how; what do we need them to do and what do they need from us; how we will keep them informed and their relative importance to success]
Project Stakeholder Engagement & Management
Who are the Stakeholders for this project/service? | How will they be impacted, include their current status? | What do we require from them? | What are their requirements? | How influential are they? |  |  | What is our engagement plan? | What is our deadline for engagement?
|  |  |  | Interest | Influence | Engagement Required
Children and young people and their families
CCGs
Public Health
Directors of Children Services

## Status List
Complete
On Target
Delayed - being monitored
Overdue - requires escalation
Not due to start
Key
Action complete
Action on target
Action is delayed but activity is being taken. It does not need to be escalated but is being carefully monitored
Action overdue and matter needs to be escalated
Action not due to start