## Notes
i-THRIVE Approach to Implementation - Implementation Plan Template
This template can be adapted by sites who are using the i-THRIVE Approach to Implementation to support their implementation of THRIVE and used as a basis for their implementation planning.
The steps outlined in this implementation plan template mirror the phases of the i-THRIVE Approach to Implementation which is an evidence based approach to implementation to enable better delivery of system change.
An overview of the i-THRIVE Approach to Implementation is set out below:
This template is a generic plan that sets out the core steps of the i-THRIVE Approach to Implementation. Sites can adapt the template to suit their local context - for instance, if they already have staff in post they can remove the recruitment tasks - and add in additional details as necessary.
For phase three of implementation sites will need to add in their own specific individual change project details and timescales. However, as a guide, there is a list of the operational elements that a site would need to have in place in order to assess themselves as 'THRIVE-like' against the THRIVE Assessment Tool (item 3.3 on the template). These should be included in the implementation plan if they are not already in existence in the local area.
If you would like to discuss using this template or any other tools from the i-THRIVE Toolkit please contact ithriveinfo@tavi-port.nhs.uk
For further information about i-THRIVE and support with implementation please visit www.implementingTHRIVE.org.

## Template
i-THRIVE Approach to Implementation - Implementation Plan Template
To be adapted by sites who are using the i-THRIVE Approach to Implementation to support their implementation of THRIVE
Further information and support can be found at www.implementingTHRIVE.org
|  | Notes / Resources Available | Year One |  |  |  | Year Two |  |  |  | Year Three |  |  |  | Year Four |  |  |  | Year Five
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Set Up
0.1 | Establish cross sector approval to proceed with i-THRIVE | bar: Year One Q1
0.2 | Recruit into posts: Clinical Lead, Project Lead (SRO), Project Manager, Project Support Officer(s), Administration Support etc as required | Support from i-THRIVE PMO | bar: Year One Q1 to Year One Q2
0.3 | Establish Programme Management Office (PMO) | Support from i-THRIVE PMO | bar: Year One Q1 to Year One Q2
0.4 | PMO structures established e.g. team meetings, learning logs, project reporting etc | Support from i-THRIVE PMO | bar: Year One Q2
0.5 | Set up multi-agency Programme Board (include senior leadership from CCG, health provider(s), local authority, education, third sector) | Support from i-THRIVE PMO | bar: Year One Q2
0.6 | Undertake stakeholder mapping | Support from i-THRIVE PMO | bar: Year One Q2
0.7 | Create communications and engagement plan based on stakeholder analysis | Support from i-THRIVE PMO | bar: Year One Q2
0.8 | Multi-agency working group established | i-THRIVE Toolkit | bar: Year One Q2
0.9 | Site leads/sponsors identified (where i-THRIVE delivered across multiple sites) | bar: Year One Q2
0.1 | Establish communications functions (contact databases, shared folders, website) | Support from i-THRIVE PMO | bar: Year One Q2
0.11 | Create high level project plan | i-THRIVE Toolkit | bar: Year One Q2 to Year One Q3
0.12 | High level project plan approved by Programme Board | bar: Year One Q3
1 | i-THRIVE Approach to Implementation Phase 1: Engagement, Understanding and Planning
1.1 | Key messaging for i-THRIVE project established - goals, aspirations, local context | bar: Year One Q2 to Year One Q3
1.2 | Whole system stakeholder engagement event | i-THRIVE Toolkit | bar: Year One Q3
1.3 | Pathway mapping workshop | i-THRIVE Toolkit | bar: Year One Q3
1.4 | Staff consultation | i-THRIVE Toolkit | bar: Year One Q3
1.5 | Young people and families consultation | bar: Year One Q3
1.6 | Qualitative review of feedback collected | bar: Year One Q3
1.7 | Service performance review (including population need, demand, flow, experience of service, participation levels, clinical outcomes, efficiency, current shared decision making practice etc) | i-THRIVE Toolkit | bar: Year One Q3
1.8 | Mapping of current outcome measures used across health, social care, education and voluntary sector | bar: Year One Q3
1.9 | Understanding your data workshop | i-THRIVE Toolkit | bar: Year One Q4
1.1 | THRIVE Assessment Tool workshop | i-THRIVE Toolkit | bar: Year One Q4 to Year Two Q1
1.11 | Engagement with wider system re THRIVE-like baseline score | bar: Year Two Q1
1.12 | Prioritisation and gap analysis workshop | i-THRIVE Toolkit | bar: Year Two Q1
1.13 | Redesign workshop | i-THRIVE Toolkit | bar: Year Two Q2
1.14 | Creation of local model for i-THRIVE | bar: Year Two Q2
1.15 | Finalise implementation plan | i-THRIVE Toolkit | bar: Year Two Q2
2 | i-THRIVE Approach to Implementation Phase 2: Building Capacity
2.1 | Review of staff skills for THRIVE-like working | bar: Year One Q4 to Year Two Q3
2.2 | Review of staff capacity for delivery of new model | bar: Year Two Q2 to Year Two Q3
2.3 | Plan for recruiting to deliver new model | bar: Year Two Q3
2.4 | Review of training opportunities available across all organisations | bar: Year Two Q3
2.5 | Creation of workforce development plan | bar: Year Two Q3 to Year Two Q4
2.6 | Development of new commissioning specification | bar: Year Two Q1 to Year Two Q4
2.7 | Identification and creation of local champions and implementation leads | bar: Year One Q4 to Year Two Q1
2.8 | Training for implementation leads (knowledge of change management, i-THRIVE Approach to Implementation and QI) | i-THRIVE Academy | bar: Year Two Q1 to Year Two Q3
2.9 | i-THRIVE Academy training for multi-agency front line staff and managers | i-THRIVE Academy | bar: Year Two Q4
| > Principles of the THRIVE conceptual framework | i-THRIVE Academy | bar: Year Two Q4
| > Getting advice: assessment and signposting | i-THRIVE Academy | bar: Year Two Q4
| > Self management and patient activation | i-THRIVE Academy | bar: Year Two Q4
| > Shared decision making | i-THRIVE Academy | bar: Year Two Q4
| > When to stop treatment | i-THRIVE Academy | bar: Year Two Q4
| > Risk support | i-THRIVE Academy | bar: Year Two Q4
2.1 | Multi-agency workshop event to reflect on learnings from i-THRIVE Academy and other training | bar: Year Three Q1
2.11 | Delivery of other training and development as set out in workforce development plan | bar: Year Three Q1 to Year Five Q4
2.12 | Review of workforce development delivery and plans for ongoing work | bar: Year Four Q1 to Year Five Q4
3 | i-THRIVE Approach to Implementation Phase 3: Implementation
3.1 | Ongoing review of implementation plan agreed at end of phase one | bar: Year Two Q3 to Year Five Q4
3.2 | Detailed implementation planning finalised with lead for each project identified | bar: Year Two Q4
3.3 | Delivery of implementation plan as specified *import detailed implementation plan into this section* The implementation plan should include - as a minimum - the following elements which are required in order for a site to be assessed as 'THRIVE-like' in line with the THRIVE Assessment Tool: | i-THRIVE Toolkit | bar: Year Two Q4 to Year Five Q4
> Children and young people's mental health is included in the LTP and the STP and implementation plan is in place for delivering outcomes | bar: Year Two Q4 to Year Five Q4
> Multi-agency strategy and policy for delivering improved outcomes for children and young people's mental health operational with clear and measureable goals | bar: Year Two Q4 to Year Five Q4
> Multi-agency commissioning board operational with joint accountability for delivering strategy | bar: Year Two Q4 to Year Five Q4
> Shared outcome framework for the multi-agency commissioning board is in place | bar: Year Two Q4 to Year Five Q4
> Annual commissioning cycle (multi-agency) operational supported by formal mechanism for service performance, outcome and preference data to inform the process | bar: Year Two Q4 to Year Five Q4
> Joint budgets to support delivery of strategy established with processes in place across all involved agencies | bar: Year Two Q4 to Year Five Q4
> Protocols established for regular sharing of performance and outcomes data across all agencies and commissioners | bar: Year Two Q4 to Year Five Q4
> Introduction of systematic preference data collection across all agencies and sectors | bar: Year Two Q4 to Year Five Q4
> All QI projects are undertaken using recognised methodology | bar: Year Two Q4 to Year Five Q4
> Outcomes and process measures are collected routinely and this data is used to help shape service provision, manage performance and deliver interventions **full list of measures is available from i-THRIVE programme team | bar: Year Two Q4 to Year Five Q4
> Local pathways structured to deliver care according to five THRIVE needs based groups | bar: Year Two Q4 to Year Five Q4
> Multi-agency assessment that categorises children and young people into the THRIVE needs based groups is operational | bar: Year Two Q4 to Year Five Q4
> THRIVE needs based group recorded for all cases | bar: Year Two Q4 to Year Five Q4
> Implementation of i-THRIVE Grids to support shared decision making | bar: Year Two Q4 to Year Five Q4
> Record of shared decision making documented for all cases | bar: Year Two Q4 to Year Five Q4
> Population health and wellbeing offer available to all children and young people | bar: Year Two Q4 to Year Five Q4
> Targeted prevention and resilience building offer available to children and young people who we know are more likely to require support with their mental health and wellbeing | bar: Year Two Q4 to Year Five Q4
> Digital front end is available for children, young people and their families | bar: Year Two Q4 to Year Five Q4
> There is a self-help and peer support offer available to children, young people and families | bar: Year Two Q4 to Year Five Q4
> Senior mental health practitioners (band 8 or above) involved in all advice and signposting | bar: Year Two Q4 to Year Five Q4
> Digitally enabled database of full range of community providers is operational | bar: Year Two Q4 to Year Five Q4
> In reach from CAMHS to schools is operational | bar: Year Two Q4 to Year Five Q4
> In reach from CAMHS to primary care is operational | bar: Year Two Q4 to Year Five Q4
> CAMHS outreach to hard to reach groups is operational | bar: Year Two Q4 to Year Five Q4
> Evidence of families being involved in development of care plans in all cases | bar: Year Two Q4 to Year Five Q4
> Evidence of therapy being aligned with NICE guidance for all cases | bar: Year Two Q4 to Year Five Q4
> Recorded note of treatment goals and expected outcomes for all cases | bar: Year Two Q4 to Year Five Q4
> Children, young people and their families are managed within the recommended number of therapy sessions | bar: Year Two Q4 to Year Five Q4
> Reasons for ending proforma completed for all cases with treatment | bar: Year Two Q4 to Year Five Q4
> Multi-agency structures and protocols for providing risk support | bar: Year Two Q4 to Year Five Q4
> Multi-agency THRIVE plans documented for all risk support cases | bar: Year Two Q4 to Year Five Q4
3.4 | Year one of implementation (details to be added) | bar: Year Two Q4 to Year Three Q3
*add individual QI projects* | bar: Year Two Q4 to Year Three Q3
*add individual QI projects* | bar: Year Two Q4 to Year Three Q3
*add individual QI projects* | bar: Year Two Q4 to Year Three Q3
*add individual QI projects* | bar: Year Two Q4 to Year Three Q3
3.5 | Year one progress review and refine plan for year two | bar: Year Three Q2 to Year Three Q4
3.6 | Year two of implementation (details to be added) | bar: Year Three Q4 to Year Four Q3
*add individual QI projects* | bar: Year Three Q4 to Year Four Q3
*add individual QI projects* | bar: Year Three Q4 to Year Four Q3
*add individual QI projects* | bar: Year Three Q4 to Year Four Q3
*add individual QI projects* | bar: Year Three Q4 to Year Four Q3
3.7 | Year two progress review and refine plan for year three | bar: Year Four Q2 to Year Four Q4
3.8 | Year three of implementation (details to be added) | bar: Year Four Q4 to Year Five Q3
*add individual QI projects* | bar: Year Four Q4 to Year Five Q3
*add individual QI projects* | bar: Year Four Q4 to Year Five Q3
*add individual QI projects* | bar: Year Four Q4 to Year Five Q3
*add individual QI projects* | bar: Year Four Q4 to Year Five Q3
3.9 | Year three progress review and refine plan for year four | bar: Year Five Q2 to Year Five Q4
3.1 | * Continue as necessary in yearly cycles* | bar: Year Five Q4
4 | i-THRIVE Approach to Implementation Phase 4: Embedding and Sustaining
4.1 | Establish learning collaborative | i-THRIVE Community of Practice model | bar: Year One Q2 to Year One Q4
4.2 | Learning collaborative | bar: Year One Q4; Year Two Q2; Year Two Q4; Year Three Q2; Year Three Q4; Year Four Q2; Year Four Q4; Year Five Q2; Year Five Q4
4.3 | Embedding and sustaining year one implementation projects | Based on Normalisation Process Theory | bar: Year Three Q2 to Year Five Q4
4.4 | Embedding and sustaining year two implementation projects | bar: Year Three Q4 to Year Five Q4
4.5 | Embedding and sustaining year three implementation projects | bar: Year Four Q2 to Year Five Q4